## Sheet1
SPRINT BACKLOG 1
SPRINT BACKLOG | US ID | AS A/AN | I WANT TO | SO THAT | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | user | Planning for design | Making plan for whole project | 1 | Prasan Gupta, Rajnish Kumar,Om Prakash | 2022-10-10
|  | user | work on designing | Creating layout and Design for requirement. | 1 | Prasan Gupta | 2022-10-10
|  | user | work on suitable design | we will have predefined flow diag | 1 | Prasan Gupta | 2022-10-10
|  | user | working on Activity | we will have predefined flow diag | 1 | Prasan Gupta | 2022-11-10
|  | user | working on Activity flow chart | we will have predefined flow diag | 1 | Om Prakash | 2022-11-10
|  | user | working on desining flow chart | we will have predefined flow diag | 1 | Om Prakash | 2022-12-10
|  | user | Linking activity together | we can hav initial abstract application flow | 1 | Prasan Gupta | 13/10/2022
|  | user | creating database framework and layout | we will have predefined flow diag and fields | 1 | Prasan Gupta | 14/10/2022
|  | user | making firestore account and dosing all configrations od backend | hence database live | 2 | Om Prakash | 15/10/2022
|  | user | Create navbar | User easly access the services | 2 | Om Prakash | 16/10/2022
|  | User | Create navbar menu | User easly access the services | 2 | Om Prakash, Prasan Gupta | 17/10/2022
|  | user | Desining Login or Signup Page | User Can Register to get benefits of Services | 3 | Om Prakash | 18/10/2022
|  | user | Working on Login or Signup page | User Can Register to get benefits of Services | 3 | Om Prakash | 18/10/2022
|  | user | Creating Login or Signup page | User Can Register to get benefits of Services | 3 | Prasan Gupta | 19/10/2022
|  | user | Register Myself Using Gmail Id | I Can Receive A Confirmation/Verification Mail | 4 | Prasan Gupta | 19/10/2022
|  | user | Receive A Confirmation Mail | I Can Access The Digital College System | 4 | Prasan Gupta | 20/10/2022
|  | user | Login Into The System Using Gmail Id And Password | I Can View/Edit My Profile | 4 | Prasan Gupta | 21/10/2022
|  | user | Modify The Account Password | I Can Keep My Account Secure | 5 | Prasan Gupta | 22/10/2022
|  | user | View my password | I Can see my password constantly | 5 | Om Prakash | 23/10/2022
|  | user | Check the category of services | User can check the sevices Details | 6 | Om Prakash | 24/10/2022
|  | user | Check the Quality of services | User can check how services is reliable | 6 | Om Prakash | 25/10/2022
|  | user | User Select the Services | I can see the responses from the user. | 6 | Om Prakash | 26/10/2022
|  | user | Adding feedback form for app improvement | I Can send feedback to the developer | 7 | Om Prakash | 27/10/2022
|  | user | Linking feedback form with app firestore | developer can easily watch those feedbacks | 7 | Rajnish Kumar | 27/10/2022
|  | user | Initial application testing | for better performance and less error | 7 | Rajnish Kumar | 28/10/2022
|  | user | Redusing identified bugs from the application | for better performance and less error | 7 | Rajnish Kumar | 28/10/2022
SPRINT BACKLOG 2
|  | user | Work on Setting | I Can manage my profile |  | Rajnish Kumar
|  | user | Work on help | I Can get a tutorial guide |  | Rajnish Kumar
|  | user | Work on about us | User can know about us |  | Prasan Gupta
|  | user | FAQ | I Can get the information related to it |  | Prasan Gupta
|  | user | logout | I Can securely logout my account |  | Prasan Gupta
|  | User | Desining footer Layout | Creating flow diagram |  | Om Prakash
|  | User | Working on Footer | we will have predefined flow diag |  | Om Prakash
|  | User | Connecting footer with the links | we will have predefined flow diag |  | Om Prakash
|  | User | Making footer responsive | we will have predefined flow diag |  | Om Prakash
|  | User | Desining Event pages | Creating flow diagram |  | Prasan Gupta
|  | User | work on suitable design | we will have predefined flow diag |  | Prasan Gupta
|  | User | working on Activity | we will have predefined flow diag |  | Prasan Gupta
|  | User | Implementing Activity pages | we will have predefined flow diag |  | Om Prakash
|  | User | Activity-Decoration | we will have predefined flow diag |  | Prasan Gupta
|  | User | Working on Decoraters for mehandi | We will add a list for All the available Decoraters |  | Prasan Gupta
|  | User | Implementing Mehandi pages | We will add a list for All the available Decoraters |  | Om Prakash
|  | User | Working on Decoraters for Haldi | We will add a list for All the available Decoraters for particular event |  | Prasan Gupta
|  | User | Implementing Haldi pages | We will add a list for All the available Decoraters for particular event |  | Om Prakash
|  | User | Working on Decoraters for Ring Ceromony | We will add a list for All the available Decoraters for particular event |  | Prasan Gupta
|  | User | Implementing Ring Ceromony pages | We will add a list for All the available Decoraters for particular event |  | Om Prakash
|  | User | Decoraters for All other small function | We will add a list for All the available Decoraters for particular event |  | Prasan Gupta
|  | User | Implementing Small Funtions pages | We will add a list for All the available Decoraters for particular event |  | Om Prakash
SPRINT BACKLOG 3
|  | User | Working on Activity-Food Catering | We will add a list for All the available Decoraters for particular event |  | Prasan Gupta
|  | User | Implementing food catering pagees | We will add a list for All the available Cateres |  | Om Prakash
|  | User | Working on Activity-Security | We will add a list for All the available Security Agents |  | Prasan Gupta
|  | User | Working on Activity-Cook for home | We will add a list for All the available Cooks(Maharaj) |  | Prasan Gupta
|  | User | Implementing Cook pages | We will add a list for All the available Cooks(Maharaj) |  | Om Prakash
|  | User | Working on Activity-Choreographer | We will add a list for All the available Dance Choreographers |  | Prasan Gupta
|  | User | Implementing Choreographer pages | We will add a list for All the available Dance Choreographers |  | Om Prakash
|  | User | Working on Acitvity-Photographer | we will add a list for All the available Photographer for particular thing |  | Prasan Gupta
|  | User | Implementing photographer pages | we will add a list for All the available Photographer for particular thing |  | Om Prakash
|  | User | Working on Pre wedding photoshoot | we will add a list for All the available Photographer for particular thing |  | Prasan Gupta
|  | User | Implementing Pre Wedding photoshoot pages | we will add a list for All the available Photographer for particular thing |  | Om Prakash
|  | User | Working on 5D photoshoot | we will add a list for All the available Photographer for particular thing |  | Prasan Gupta
|  | User | Implementing 5D photoshoot | we will add a list for All the available Photographer for particular thing |  | Om Prakash
|  | User | Working on Simple Photoshoot | we will add a list for All the available Photographer for particular thing |  | Prasan Gupta
|  | User | Implementing Simple Photoshoot | we will add a list for All the available Photographer for particular thing |  | Om Prakash
|  | User | Candid Photoshoot | we will add a list for All the available Photographer for particular thing |  | Prasan Gupta
|  | User | Albums | we will add a list for All the available Photographer for particular thing |  | Prasan Gupta
|  | User | Linking conatact between planner & user | you will get to contact the delivery person |  | Rajnish Kumar
SPRINT BACKLOG 4
|  | User | Storing data while signup | Data store at backend |  | Om Prakash
|  | User | Storing Mail id | Data store at backend |  | Om Prakash
|  | User | Storing password | Data store at backend |  | Om Prakash
|  | User | Storing name | Data store at backend |  | Om Prakash
|  | User | Storing Mobile number | Data store at backend |  | Om Prakash
|  | User | Storing location for Event | Data store at backend |  | Rajnish Kumar
|  | User | storing data of venue | Data store at backend |  | Rajnish Kumar
|  | User | Storing data of total members | Data store at backend |  | Rajnish Kumar
|  | User | Storing data of Decorator | Data store at backend |  | Rajnish Kumar
|  | User | Storing Data of Selected Photographer | Data store at backend |  | Rajnish Kumar
|  | User | Storing data of Cook | Data store at backend |  | Rajnish Kumar
|  | User | Storing Data of caters | Data store at backend |  | Om Prakash
|  | User | Storing data of Waiters | Data store at backend |  | Om Prakash
|  | User | Storing Data of Choreographer & Anchor | Data store at backend |  | Om Prakash
|  | User | Storing Data of Travelling organizer | Data store at backend |  | Rajnish Kumar
|  | User | The information sharing of Event date | Using data from database |  | Rajnish Kumar
|  | User | Generating a Linking Between All the organizing Team | Using data from database |  | Rajnish Kumar
|  | User | Maintaine the Reviews of Customer | Using data from database |  | Rajnish Kumar
|  | User | Using different method for leveling up the site | Create MySQL Table |  | Rajnish Kumar
|  | User | Creating Table for Decorators | Create MySQL Table |  | Om Prakash
|  | User | Creating Table for Photographers | Create MySQL Table |  | Om Prakash
|  | User | Creating Table for Available venue | Create MySQL Table |  | Om Prakash
|  | User | Creating Table for Caters | Create MySQL Table |  | Om Prakash
|  | User | Creating Table for All Traveling Agents | Create MySQL Table |  | Rajnish Kumar
|  | User | Creating Table for Choreographer | Create MySQL Table |  | Rajnish Kumar
|  | User | Verifying Credential at Login Time | Using data from database |  | Rajnish Kumar
|  | User | Verify Password | Using data from database |  | Om Prakash
|  | User | Verify Email | Using data from database |  | Om Prakash
|  | User | Testing The Backend inputing the data | Using data from database |  | Rajnish Kumar