## Sheet1
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Wedding Event Catalog>
SB3/US1 | Designing of the Login page table so that user can login and enter their valid credential. | SB3/US1/T1 | Designing of GUI | OP+RK+PG | Completed | 2023-10-01
|  | SB3/US1/T2 | Validating user input at client level | OP+RK | Completed | 2023-11-01
|  | SB3/US1/T3 | Validating user input at server level | OP+RK | Completed | 2023-12-01
|  | SB3/US1/T4 | Connection with Database to insert the record. | OP+RK | Completed | 13/01/2023
|  | SB3/US1/T5 | Testing of the module on localhost and then on server. | RK+OP+PG | Completed | 15/01/2023
SB3/US2 | Designing of the Sinup page table so that user can register. | SB3/US2/T1 | Designing of GUI | OP+RK+PG | Completed | 18/01/2023
|  | SB3/US2/T2 | Validating user input at client level | RK+OP | Completed | 19/01/2023
|  | SB3/US2/T3 | Validating user input at server level | OP+RK | Completed | 20/01/2023
|  | SB3/US2/T4 | Connection with Database to insert the record. | OP+RK | Completed | 21/01/2023
|  | SB3/US2/T5 | Testing of the module on localhost and then on server. | OP+RK+PG | Completed | 23/01/2023
SB3/US3 | Desiging of the Contact us Page table so that user can easily contact with admin. | SB3/US5/T1 | Designing the GUI | OP+PG+RK | Completed | 20/02/2023
|  | SB3/US5/T2 | Validating user input at client level | OP+RK | Completed | 21/02/2023
|  | SB3/US5/T3 | Validating user input at server level | RK+OP | Completed | 22/02/2023
|  | SB3/US5/T4 | Connection with Database to insert the record. | OP+RK | Completed | 23/02/2023
|  | SB3/US5/T5 | Testing of the module on localhost and then on server. | OP+RK+PG | Completed | 25/02/2023