## Sheet1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SGRINT 1 - <Wedding Event Catalog>
SB1/US1 | Planning and Designing Activity Diagram so that we can work smoothly on the project | SB1/US1/T1 | Making plan for whole project | OP+PG+RK | Completed | 2022-10-10
|  | SB1/US1/T2 | Creating layout and Design for requirement. | PG+OP | Completed | 2022-10-10
|  | SB1/US1/T3 | Working on Activity Diagram | PG+OP | Completed | 2022-11-10
|  | SB1/US1/T4 | Working on Activity flow Diagram | PG | Completed | 2022-11-10
|  | SB1/US1/T5 | Linking the Activity in the web pages | OP+RK | Completed | 2022-12-10
|  | SB1/US1/T6 | we will have predefined flow diag | RK | Completed | 13/10/2022
SB1/US2 | Designing of the Header of the page and the navbar in order to provide better user experience | SB1/US2/T1 | Planning of Navbar Design and fields | OP+RK | Completed | 14/10/2022
|  | SB1/US2/T2 | we will have predefined flow diag and fields | OP+RK | Completed | 15/10/2022
|  | SB1/US2/T3 | Designing the GUI | OP+RK | Completed | 16/10/2022
|  | SB1/US2/T4 | Designing of Login Button | OP+RK | Completed | 17/10/2022
|  | SB1/US2/T5 | Testing of the module on localhost | OP+RK | Completed | 18/10/2022
SB1/US3 | Desiging of the landing page so that we can provide better idea about the site. | SB1/US3/T1 | Planning of landing page | OP+RK | Completed | 19/10/2022
|  | SB1/US3/T2 | Designing of landing page | RK | Completed | 20/10/2022
|  | SB1/US3/T3 | Landing page content gathering | RK | Completed | 22/10/2022
|  | SB1/US3/T4 | Linking of page with javascript to display the real-time | RK | Completed | 25/10/2022
|  | SB1/US3/T5 | Testing of the module on localhost | OP+RK | Completed | 26/10/2022
SB1/US4 | Footer designing of the landing page so that user can have a better experience | SB1/US4/T1 | Planning of the footer design | RK | Completed | 27/10/2022
|  | SB1/US4/T2 | Designing the GUI | RK | Completed | 28/10/2022
|  | SB1/US4/T3 | Linking the footer with the header page | RK | Completed | 30/10/2022
|  | SB1/US4/T4 | Testing of the module on localhost | OP+RK | Completed | 31/10/2022
SB1/US5 | Desiging of the Login Page so that user can easily access the service and to provide better security | SB1/US5/T1 | Planning of the Login Page Design | OP+RK | Completed | 2022-01-10
|  | SB1/US5/T2 | Designing of login page | OP+RK | Completed | 2022-02-10
|  | SB1/US5/T3 | Validating the input fields at client level | RK | Completed | 2022-03-10
|  | SB1/US5/T4 | Testing of the module on localhost | RK | Completed | 2022-05-10