## Sheet1
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Wedding Event Catalog>
SB2/US1 | Designing of the Contatct us page so the user can easily contact us if any additional information required | SB2/US1/T1 | Planning of Contact us page | OP+RK+PG | Completed | 07/112022
|  | SB2/US1/T2 | Designing of Contact us page | OP+RK | Completed | 08/112022
|  | SB2/US1/T3 | Contact us form creation | OP+RK+PG | Completed | 09/112022
|  | SB2/US1/T4 | Validating the input fields at client level | OP+RK | Completed | 10/112022
|  | SB2/US1/T5 | Linking of contact us page with header and footer | RK | Completed | 2022-11-11
|  | SB2/US1/T6 | Testing of the module on localhost | OP+RK | Completed | 2022-12-11
SB2/US2 | Designing of the FAQ page so that user can easily get the answer of the frequently asked question | SB2/US2/T1 | Planning of FAQ page | OP+RK | Completed | 13/11/2022
|  | SB2/US2/T2 | Landing page content gathering | RK | Completed | 14/11/2022
|  | SB2/US2/T3 | Designing of FAQ page | OP+RK | Completed | 15/11/2022
|  | SB2/US2/T4 | Linking of FAQ page with header and footer | OP+RK | Completed | 16/11/2022
|  | SB2/US2/T5 | Testing of the module on localhost | OP+RK | Completed | 17/11/2022
SB2/US3 | Desiging of the Resistration Page so that user can easily access the service and to provide better security | SB1/US5/T1 | Planning of the Registration Page Design | OP+PG+RK | Completed | 18/11/2022
|  | SB1/US5/T2 | Designing of Registration page | OP+RK | Completed | 19/11/2022
|  | SB1/US5/T3 | Validating the input fields at client level | RK | Completed | 20/11/2022
|  | SB1/US5/T4 | Testing of the module on localhost | OP | Completed | 21/11/2022
SB2/US4 | Designer of the Wedding Organiser Page in order to meet the user requirement and provide the best possible services | SB2/US1/T1 | Planning of Organiser page | OP+RK+PG | Completed | 22/112022
|  | SB2/US1/T2 | Designing of Organiser page | OP+RK | Completed | 23/112022
|  | SB2/US1/T3 | Landing page content gathering | OP+RK+PG | Completed | 24/112022
|  | SB2/US1/T4 | Validating the input fields at client level | OP+RK | Completed | 25/112022
|  | SB2/US1/T5 | Linking of Organiser page with header and footer | RK | Completed | 27/11/2022
|  | SB2/US1/T6 | Testing of the module on localhost | OP+RK | Completed | 28/11/2022